Sample Reporting Structure and Integration Plan for Early Childhood Development Expert

Position: Early Childhood Development (ECD) Expert
Department: Pediatrics /Family Health / Behavioral Health Integration (depending on community health center structure)
Reports To: Director of Integrated Services or Clinical Director
Collaborates Closely With:

- Pediatric Medical Providers (MDs, DOs, NPs, PAs)

- Behavioral Health Providers (LCSWs, psychologists)

- Care Coordinators / Case Managers

- Community Health Workers (CHWs)

- Nurses / Medical Assistants

- Front Desk and Scheduling Teams

- Health Educators / Family Navigators

Phase 1: Orientation and Role Definition (Weeks 1-4)

- Meet with leadership to understand clinical goals, priorities, and patient demographics.

- Shadow pediatric well-child visits to understand existing workflows.

- Review current use of developmental tools (e.g., Ages & Stages Questionnaires, Bright Futures).

- Define scope of responsibilities with input from the care team (e.g., whether the ECD Expert will support all visits, targeted age ranges, or high-risk families).

- Develop a shared understanding with providers about when and how to involve the ECD Expert during visits.

Phase 2: Pilot Integration (Month 2-3)

- Start small: Embed the ECD Expert into one pediatric provider's well-child visit schedule (e.g., 0-3 age range).

- ECD Expert participates in pre-visit planning huddles, reviewing charts and identifying opportunities for engagement (e.g., screening needs, developmental red flags).

- During visits, ECD Expert can:

  - Conduct or interpret developmental screenings.

  - Offer anticipatory guidance (e.g., sleep, language, behavior).

  - Provide parent handouts in preferred languages.

  - Refer to community resources as needed.

- Post-visit, ECD Expert documents interactions in the electronic health record (EHR) and updates relevant care plans.

Phase 3: Feedback and Workflow Adjustment (Month 3-4)

- Hold bi-weekly huddles with the pilot provider and care team to:

  - Review patient/family feedback.

  - Evaluate handoffs, documentation process, and integration flow.

  - Troubleshoot barriers (e.g., time constraints, role clarity).

- Adjust responsibilities as needed (e.g., expanding ECD involvement in behavioral health consultations or group visits).

Phase 4: Scale Up (Month 5-6)

- Expand ECD Expert support to additional providers or care teams, focusing on:

  - High-risk families (e.g., preterm birth, housing insecurity, parental mental health needs).

  - Specific age groups (e.g., 9-month and 18-month visits tied to key milestones).

- ECD Expert may begin co-leading parent workshops or developmental education groups with health educators or CHWs.

Phase 5: Sustain & Evolve

- Include the ECD Expert in:

  - Quality improvement efforts related to child development.

  - Staff training and onboarding of new team members.

  - Community partnership meetings (e.g., early intervention agencies, Head Start).

- Establish a formal evaluation plan tracking outcome such as:

  - Developmental screening rates.

  - Referral follow-through.

  - Family satisfaction with care.

  - Provider feedback on ECD expert support.